## Dashboard
Construction Dashboard
Project Name
Timeline Start
Weeks Shown
Key Metrics
Total Tasks
Completed Tasks
In Progress
Blocked
Avg % Complete

## Construction Gantt
Construction Gantt (Phases + Trades) — Weekly Schedule
Setup
Project Name | Example: 123 Main St Office Build |  | Legend
Timeline Start (Monday) | 2026-01-05 |  | Green | Completed portion
Weeks Shown | 26 |  | Phase color | Remaining portion (by phase)
Tip: Change Weeks Shown to show/hide columns (unhide extra weeks if needed).
WBS | Phase | Trade | Task / Deliverable | Area / Location | Start | End | Duration (days) | % Complete | Status | Owner | Predecessors | Notes | Complete Thru (calc) | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20 | Wk 21 | Wk 22 | Wk 23 | Wk 24 | Wk 25 | Wk 26 | Wk 27 | Wk 28 | Wk 29 | Wk 30 | Wk 31 | Wk 32 | Wk 33 | Wk 34 | Wk 35 | Wk 36 | Wk 37 | Wk 38 | Wk 39 | Wk 40 | Wk 41 | Wk 42 | Wk 43 | Wk 44 | Wk 45 | Wk 46 | Wk 47 | Wk 48 | Wk 49 | Wk 50 | Wk 51 | Wk 52
1.0 | Preconstruction |  | Preconstruction
1.1 | Preconstruction | GC | Permitting & approvals | City / AHJ | 2026-01-05 | 2026-01-25 |  | 25% | In Progress | PM
1.2 | Preconstruction | GC | Subcontractor buyout | Office | 2026-01-12 | 2026-01-26 |  | 0% | Not Started | PM | 1.1
2.0 | Sitework |  | Sitework
2.1 | Sitework | Earthwork | Mobilize + layout | Site | 2026-01-26 | 2026-01-30 |  | 0% | Not Started | Super
2.2 | Sitework | Earthwork | Excavation | Site | 2026-01-31 | 2026-02-09 |  | 0% | Not Started | Super | 2.1
3.0 | Foundation |  | Foundation
3.1 | Foundation | Concrete | Form + pour footings | Site | 2026-02-10 | 2026-02-19 |  | 0% | Not Started | Concrete Foreman | 2.2
3.2 | Foundation | Concrete | Slab on grade | Site | 2026-02-20 | 2026-03-01 |  | 0% | Not Started | Concrete Foreman | 3.1
4.0 | Structure/Framing |  | Structure/Framing
4.1 | Structure/Framing | Steel | Erect structural steel | Building | 2026-03-02 | 2026-03-16 |  | 0% | Not Started | Steel Foreman | 3.2
4.2 | Structure/Framing | Carpentry | Exterior framing | Building | 2026-03-10 | 2026-03-24 |  | 0% | Not Started | Carpentry Lead | 4.1
5.0 | MEP Rough-In |  | MEP Rough-In
5.1 | MEP Rough-In | Plumbing | Underground plumbing | Building | 2026-03-06 | 2026-03-20 |  | 0% | Not Started | Plumbing Lead | 3.2
5.2 | MEP Rough-In | Electrical | Electrical rough-in | Building | 2026-03-18 | 2026-04-10 |  | 0% | Not Started | Electrical Lead | 4.2
5.3 | MEP Rough-In | Mechanical | HVAC rough-in | Building | 2026-03-18 | 2026-04-10 |  | 0% | Not Started | Mechanical Lead | 4.2
6.0 | Envelope |  | Envelope
6.1 | Envelope | Carpentry | Windows & doors install | Building | 2026-03-25 | 2026-04-07 |  | 0% | Not Started | Envelope Lead | 4.2
6.2 | Envelope | GC | Roofing | Building | 2026-03-25 | 2026-04-05 |  | 0% | Not Started | Envelope Lead | 4.2
7.0 | Interiors/Finishes |  | Interiors/Finishes
7.1 | Interiors/Finishes | Drywall | Hang + finish drywall | Building | 2026-04-11 | 2026-05-03 |  | 0% | Not Started | Drywall Lead | 5.2
7.2 | Interiors/Finishes | Painting | Prime + paint | Building | 2026-04-25 | 2026-05-15 |  | 0% | Not Started | Painting Lead | 7.1
7.3 | Interiors/Finishes | Flooring | Flooring install | Building | 2026-05-06 | 2026-05-20 |  | 0% | Not Started | Flooring Lead | 7.2
8.0 | Commissioning/Closeout |  | Commissioning/Closeout
8.1 | Commissioning/Closeout | Inspections | Final inspections | Building | 2026-05-21 | 2026-05-30 |  | 0% | Not Started | PM | 7.3
8.2 | Commissioning/Closeout | GC | Punch list + turnover | Building | 2026-05-31 | 2026-06-14 |  | 0% | Not Started | PM | 8.1

## Lookups
Phases | Trades | Statuses
Preconstruction | GC | Not Started
Sitework | Survey | In Progress
Foundation | Earthwork | Blocked
Structure/Framing | Concrete | On Hold
MEP Rough-In | Steel | Complete
Envelope | Carpentry
Interiors/Finishes | Mechanical
FF&E | Electrical
Commissioning/Closeout | Plumbing
Fire Protection
Drywall
Flooring
Painting
HVAC Controls
Landscaping
Inspections