## Setup
Marketing Campaign Gantt (Channels + Launch)
Campaign Name | Spring Promo Launch
Timeline Start (Mon) | 2026-01-05
Weeks Shown | 26
Target Launch Date | 2026-03-02
Currency | USD
Budget (Total) | 50000
Primary KPI | Leads
Secondary KPI | CPA

## Lookups
Lookup Lists (edit to customize dropdowns)
Status | Phase | Channel | Priority | Risk | Team
Not Started | Strategy | Paid Search | Low | Low | Marketing
In Progress | Planning | Paid Social | Medium | Medium | Growth
Blocked | Creative | Display | High | High | Design
On Hold | Build | Email | Critical |  | Content
Complete | QA | SEO |  |  | Web
| Launch | Content |  |  | Engineering
| Optimize | PR |  |  | Analytics
| Post-Launch | Influencer |  |  | Legal
|  | Affiliate |  |  | Agency/Vendor
Website/Landing Page
Tracking/Analytics
Creative Ops
Legal/Compliance

## Plan
Campaign Plan (Edit tasks here — Gantt and Dashboard update automatically)
ID | Phase | Channel | Workstream / Deliverable | Owner | Team | Start | End | Duration (days) | % Complete | Status | Priority | Risk | Budget | KPI Target | Dependencies (IDs) | Notes | Baseline Start | Baseline End | Complete Thru
M-001 | Strategy | Tracking/Analytics | Measurement plan + event schema | Analytics Lead | Analytics | 2026-01-05 | 2026-01-09 | 5 | 35% | In Progress | High | Medium | 0 | Leads tracking ready |  | Define conversion events + UTMs | 2026-01-05 | 2026-01-09 | 2026-01-06
M-002 | Planning | Website/Landing Page | Landing page wireframes | UX Designer | Design | 2026-01-06 | 2026-01-13 | 8 | 0% | Not Started | High | Low | 0 | LP CVR target |  |  | 2026-01-06 | 2026-01-13 | 2026-01-06
M-003 | Creative | Paid Social | Ad creative concepts (5 angles) | Creative Lead | Design | 2026-01-08 | 2026-01-16 | 9 | 0% | Not Started | High | Medium | 0 | CTR |  |  | 2026-01-08 | 2026-01-16 | 2026-01-08
M-004 | Build | Website/Landing Page | Landing page build + tracking tags | Web Dev | Web | 2026-01-14 | 2026-01-27 | 14 | 0% | Not Started | Critical | Medium | 0 | Page speed | M-002 |  | 2026-01-14 | 2026-01-27 | 2026-01-14
M-005 | QA | Tracking/Analytics | End-to-end QA (pixels, postbacks, forms) | QA | Engineering | 2026-01-28 | 2026-02-03 | 7 | 0% | Not Started | Critical | High | 0 | 0 critical bugs | M-001,M-004 |  | 2026-01-28 | 2026-02-03 | 2026-01-28
M-006 | Launch | Paid Search | Search campaigns build + QA | SEM Manager | Marketing | 2026-01-20 | 2026-02-07 | 19 | 0% | Not Started | High | Medium | 15000 | CPA | M-004 |  | 2026-01-20 | 2026-02-07 | 2026-01-20
M-007 | Launch | Paid Social | Social campaigns build + QA | Paid Social Manager | Marketing | 2026-01-20 | 2026-02-07 | 19 | 0% | Not Started | High | Medium | 20000 | CPA | M-003,M-004 |  | 2026-01-20 | 2026-02-07 | 2026-01-20
M-008 | Launch | Email | Email sequences (3 sends) | Lifecycle Marketer | Marketing | 2026-02-03 | 2026-02-14 | 12 | 0% | Not Started | Medium | Low | 0 | Open rate |  |  | 2026-02-03 | 2026-02-14 | 2026-02-03
M-009 | Launch | PR | Press release + outreach list | PR Manager | Marketing | 2026-02-10 | 2026-02-24 | 15 | 0% | Not Started | Medium | Medium | 3000 | Mentions |  |  | 2026-02-10 | 2026-02-24 | 2026-02-10
M-010 | Launch | Content | Launch blog post + FAQ | Content Strategist | Content | 2026-02-10 | 2026-02-28 | 19 | 0% | Not Started | High | Low | 0 | Organic traffic |  |  | 2026-02-10 | 2026-02-28 | 2026-02-10
M-011 | Launch | Affiliate | Affiliate kit + tracking links | Affiliate Manager | Marketing | 2026-02-10 | 2026-02-28 | 19 | 0% | Not Started | Medium | Low | 5000 | Partners onboarded | M-001 |  | 2026-02-10 | 2026-02-28 | 2026-02-10
M-012 | Launch | Legal/Compliance | Legal review (LP, ads, disclosures) | Legal | Legal | 2026-02-03 | 2026-02-21 | 19 | 0% | Not Started | Critical | High | 0 | Approval |  |  | 2026-02-03 | 2026-02-21 | 2026-02-03
M-013 | Optimize | Paid Search | Search optimization (week 1-4) | SEM Manager | Marketing | 2026-03-02 | 2026-03-27 | 26 | 0% | Not Started | Medium | Low | 0 | CPA improvement | M-006 |  | 2026-03-02 | 2026-03-27 | 2026-03-02
M-014 | Optimize | Paid Social | Creative rotation + scaling (week 1-4) | Paid Social Manager | Marketing | 2026-03-02 | 2026-03-27 | 26 | 0% | Not Started | Medium | Low | 0 | CPA improvement | M-007 |  | 2026-03-02 | 2026-03-27 | 2026-03-02
M-015 | Post-Launch | Tracking/Analytics | Post-launch report + learnings | Analytics Lead | Analytics | 2026-03-30 | 2026-04-10 | 12 | 0% | Not Started | Medium | Low | 0 | Report delivered | M-013,M-014 |  | 2026-03-30 | 2026-04-10 | 2026-03-30
Formulas:
Complete Thru = IF(OR([Start]="",[End]="",J4=""),"",[Start]+ROUND(([End]-[Start])*J4,0))

## Gantt
Gantt View (Weekly) — Baseline (gray) • Planned (blue) • Completed (green) • Today highlight
Timeline Start | 2026-01-05 |  | Weeks Shown | 26 |  | Today | 2026-01-05
[6 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
ID | Workstream / Deliverable | Channel | Owner | Status | % | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29
M-001 | Measurement plan + event schema | Tracking/Analytics | Analytics Lead | In Progress | 35%
M-002 | Landing page wireframes | Website/Landing Page | UX Designer | Not Started | 0%
M-003 | Ad creative concepts (5 angles) | Paid Social | Creative Lead | Not Started | 0%
M-004 | Landing page build + tracking tags | Website/Landing Page | Web Dev | Not Started | 0%
M-005 | End-to-end QA (pixels, postbacks, forms) | Tracking/Analytics | QA | Not Started | 0%
M-006 | Search campaigns build + QA | Paid Search | SEM Manager | Not Started | 0%
M-007 | Social campaigns build + QA | Paid Social | Paid Social Manager | Not Started | 0%
M-008 | Email sequences (3 sends) | Email | Lifecycle Marketer | Not Started | 0%
M-009 | Press release + outreach list | PR | PR Manager | Not Started | 0%
M-010 | Launch blog post + FAQ | Content | Content Strategist | Not Started | 0%
M-011 | Affiliate kit + tracking links | Affiliate | Affiliate Manager | Not Started | 0%
M-012 | Legal review (LP, ads, disclosures) | Legal/Compliance | Legal | Not Started | 0%
M-013 | Search optimization (week 1-4) | Paid Search | SEM Manager | Not Started | 0%
M-014 | Creative rotation + scaling (week 1-4) | Paid Social | Paid Social Manager | Not Started | 0%
M-015 | Post-launch report + learnings | Tracking/Analytics | Analytics Lead | Not Started | 0%

## Dashboard
Campaign Dashboard
Total Tasks |  | Complete | In Progress | Blocked
15 |  | 0 | 1 | 0
On Hold |  | Not Started | Overall % Complete | Total Budget
0 |  | 14 | 2.333% | 43000
Status Breakdown
Status | Count
Not Started | 14
In Progress | 1
Blocked | 0
On Hold | 0
Complete | 0

## README
How to Use (Quick Start)
1) Setup: set Campaign Name, Timeline Start (Monday), Weeks Shown, Target Launch Date, Currency, and Budget.
2) Plan: add/edit tasks. Use dropdowns for Phase, Channel, Team, Status, Priority, Risk.
3) Enter Start/End dates and % Complete. Duration and Complete Thru update automatically.
4) Baseline Start/End capture your original plan (optional).
5) Gantt: Baseline (gray), Planned (blue), Completed (green), Today highlight.
6) Dashboard: live status counts and total budget.