## Software Gantt
Software Development Gantt (Sprints + Releases)
Project Setup
Project Name | Example: Web Platform Release
Timeline Start (Mon) | 2026-01-05
Sprint Length (weeks) | 2 |  | Sprint Days | 14
Sprints Shown | 16 |  | Template Max Sprints | 24
Today | 2026-01-05
Legend: | Complete | Remaining
[14 empty] | 2026-01-05 | 2026-01-19 | 2026-02-02 | 2026-02-16 | 2026-03-02 | 2026-03-16 | 2026-03-30 | 2026-04-13 | 2026-04-27 | 2026-05-11 | 2026-05-25 | 2026-06-08 | 2026-06-22 | 2026-07-06 | 2026-07-20 | 2026-08-03 | 2026-08-17 | 2026-08-31 | 2026-09-14 | 2026-09-28 | 2026-10-12 | 2026-10-26 | 2026-11-09 | 2026-11-23
[14 empty] | 2026-01-18 | 2026-02-01 | 2026-02-15 | 2026-03-01 | 2026-03-15 | 2026-03-29 | 2026-04-12 | 2026-04-26 | 2026-05-10 | 2026-05-24 | 2026-06-07 | 2026-06-21 | 2026-07-05 | 2026-07-19 | 2026-08-02 | 2026-08-16 | 2026-08-30 | 2026-09-13 | 2026-09-27 | 2026-10-11 | 2026-10-25 | 2026-11-08 | 2026-11-22 | 2026-12-06
ID | Epic | Feature / Story | Owner | Team | Release | Start | End | Duration (days) | % Complete | Status | Dependencies | Notes | CompleteThru | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24
Sprint Start | [13 empty] | 2026-01-05 | 2026-01-19 | 2026-02-02 | 2026-02-16 | 2026-03-02 | 2026-03-16 | 2026-03-30 | 2026-04-13 | 2026-04-27 | 2026-05-11 | 2026-05-25 | 2026-06-08 | 2026-06-22 | 2026-07-06 | 2026-07-20 | 2026-08-03 | 2026-08-17 | 2026-08-31 | 2026-09-14 | 2026-09-28 | 2026-10-12 | 2026-10-26 | 2026-11-09 | 2026-11-23
Sprint End | [13 empty] | 2026-01-18 | 2026-02-01 | 2026-02-15 | 2026-03-01 | 2026-03-15 | 2026-03-29 | 2026-04-12 | 2026-04-26 | 2026-05-10 | 2026-05-24 | 2026-06-07 | 2026-06-21 | 2026-07-05 | 2026-07-19 | 2026-08-02 | 2026-08-16 | 2026-08-30 | 2026-09-13 | 2026-09-27 | 2026-10-11 | 2026-10-25 | 2026-11-08 | 2026-11-22 | 2026-12-06
1 | Planning | Requirements & scope | PM | Product | R1 | 2026-01-05 | 2026-01-16 | 12 | 60% | In Progress |  | Finalize MVP scope | 2026-01-11 14:24 | bar: 2026-01-18
2 | Design | UX/UI wireframes | Designer | Design | R1 | 2026-01-12 | 2026-01-23 | 12 | 30% | In Progress | 1 |  | 2026-01-15 07:12 | bar: 2026-01-18 to 2026-02-01
3 | Build | Backend API endpoints | Backend Lead | Engineering | R1 | 2026-01-19 | 2026-02-13 | 26 | 0% | Not Started | 1 |  | 2026-01-19 | bar: 2026-02-01 to 2026-02-15
4 | Build | Frontend implementation | Frontend Lead | Engineering | R1 | 2026-01-19 | 2026-02-27 | 40 | 0% | Not Started | 2,3 |  | 2026-01-19 | bar: 2026-02-01 to 2026-03-01
5 | QA | Regression + UAT | QA Lead | QA | R1 | 2026-02-17 | 2026-03-06 | 18 | 0% | Not Started | 3,4 |  | 2026-02-17 | bar: 2026-03-01 to 2026-03-15
6 | Release | Hardening + deploy | DevOps | DevOps | R1 | 2026-03-02 | 2026-03-13 | 12 | 0% | Not Started | 5 | Release notes + rollout | 2026-03-02 | bar: 2026-03-15
Formulas:
CompleteThru = IF(AND([Start]<>"",[End]<>""),[Start]+(J15*([End]-[Start])), "")

## Lookups
Statuses | Teams | Releases
Not Started | Product | R1
In Progress | Design | R2
Blocked | Engineering | R3
On Hold | QA | Hotfix
Complete | Data
Security
DevOps

## Dashboard
Sprint / Release Dashboard
Overall Task Status
Not Started | 4 | Overall % Complete | 15%
In Progress | 2
Blocked | 0
On Hold | 0
Complete | 0
Total Tasks | 6