## Weekly Gantt
Weekly Sprint Project Gantt (Classic)
Project Name | Short Sprint Project |  | Legend
Timeline Start (Monday) | 2026-01-05 |  | Completed
Weeks Shown | 12 |  | Remaining
Sprint Length (weeks) | 1 |  | Current Week
Tip: Enter tasks (blue text). Bars update automatically. Adjust start date + weeks in Setup. | [14 empty] | Timeline (Weeks)
|  |  | On Hold | [11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
ID | Sprint | Epic/Feature | Task | Owner | Start | End | Duration (days) | % Complete | Status | Dependencies | Notes | Start Week | End Week | Complete Thru Week | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23
1 | 1 | Planning | Kickoff & scope |  | 2026-01-05 | 2026-01-09 | 5 | 25% | In Progress |  |  | 1 | 1 | 1
2 | 1 | Planning | Requirements & user stories |  | 2026-01-05 | 2026-01-16 | 12 | 10% | In Progress |  |  | 1 | 2 | 1
3 | 2 | Design | Wireframes |  | 2026-01-12 | 2026-01-23 | 12 | 0% | Not Started | 2 |  | 2 | 3 | 1
4 | 3 | Build | Core development |  | 2026-01-19 | 2026-02-13 | 26 | 0% | Not Started | 3 |  | 3 | 6 | 2
5 | 5 | QA | Testing & bugfix |  | 2026-02-09 | 2026-02-27 | 19 | 0% | Not Started | 4 |  | 6 | 8 | 5
6 | 6 | Launch | Deploy & monitoring |  | 2026-03-02 | 2026-03-06 | 5 | 0% | Not Started | 5 |  | 9 | 9 | 8

## Instructions
How to use this Weekly Sprint Gantt
1) Edit the yellow Setup cells on the Weekly Gantt sheet (Project Name, Timeline Start, Weeks Shown, Sprint Length).
2) Enter your tasks in the blue-text columns (ID, Sprint, Epic/Feature, Task, Owner, Start, End, % Complete, Status).
3) Status dropdown options: Not Started, In Progress, Blocked, On Hold, Complete.
4) The Gantt area fills automatically by week. Green shows completed portion; blue shows remaining.
5) To extend the timeline, copy the last week column to the right; to add more tasks, copy an existing formatted row downward.